## Summary
Artifact | BLS Prime canonical feature/user-story tracker
Generated | 2026-06-21
Source of truth | Current code in blsprime-fin plus BLS_PRIME_PRODUCT_OVERVIEW.md
Total feature stories | 72
Current phase | Inventory complete; automated gates and public browser smoke run; authenticated workspace browser pass pending env/test account
Canonical file | docs/BLS_Prime_feature_user_story_status.xlsx
Latest automated result | RUN-002 passed; RUN-003 passed; RUN-005 passed after pyproject temp fix
Open blocking issues | ISS-001 manual/browser pass incomplete; ISS-003 authenticated workspace needs configured test account/storage
Latest browser result | RUN-006 passed public/unauthenticated smoke; authenticated /app stories pending ISS-003

## Feature Stories
ID | Area | Feature | User Story | Expected Behavior | Primary Route/API | Source Evidence | Priority | Feature Status | Test Status | Last Test Evidence | Open Issues | Owner Notes
BLS-001 | Public landing | Spanish-first public homepage | As a visitor, I want a plain Spanish explanation of BLS Prime so I can understand the service before logging in. | The home route presents BLS Prime as a market and portfolio reading service, defaults to Spanish unless English is preferred, and avoids generic SaaS/technical wording. | / | app/page.js; components/public-home-experience.jsx; app/home-page.module.css | P1 | Inventoried; smoke-tested | Browser smoke pass | RUN-006
BLS-002 | Public landing | Language toggle and persistence | As a bilingual visitor, I want to switch EN/ES and have that choice remembered. | Language buttons update visible copy and persist the selected language in localStorage under blsprime_language_preference. | / | components/public-home-experience.jsx; components/language-layer.jsx | P1 | Inventoried; smoke-tested | Browser smoke pass | RUN-006
BLS-003 | Public landing | Public navigation | As a visitor, I want clear links to product explanation, Macro Brain, FactorLab, login, and get-started actions. | Navbar links route to the public sections or authenticated/intended destinations without broken links. | / | components/public-home-experience.jsx; app/macro-brain/page.js; app/factorlab/page.js; app/login/page.js | P1 | Inventoried; smoke-tested | Browser smoke pass | RUN-006
BLS-004 | Public landing | Interactive workspace preview | As a visitor, I want to preview the decision workspace before signing in. | Preview sidebar/tabs switch between summary, inputs, risk, checks, reading, and plan panels without layout breakage. | / | components/public-home-experience.jsx; app/home-page.module.css | P1 | Inventoried; smoke-tested | Browser smoke pass | RUN-006
BLS-005 | Legal/disclaimer | Terms page | As a user, I want terms and disclaimers available from the app. | Terms route loads and communicates service terms/disclaimer without requiring workspace access. | /terms | app/terms/page.js | P1 | Inventoried; smoke-tested | Browser smoke pass | RUN-006
BLS-006 | Recovery | Browser recovery route | As a user with stale browser state, I want a recovery route that clears service workers/caches. | Recover route serves a technical cleanup path for stale clients. | /recover | app/recover/route.js; README.md | P1 | Inventoried; smoke-tested | Browser smoke pass | RUN-006
BLS-007 | Authentication | Login and account creation | As a user, I want to log in or create an account with email/password. | Login page posts to auth route, validates email/password, creates/loads a session, and redirects to next/app on success. | /login | app/login/page.js; app/api/auth/login/route.js; lib/server/auth/session.js | P1 | Inventoried; smoke-tested | Browser smoke pass | RUN-006
BLS-008 | Authentication | Next redirect handling | As a user following a protected deep link, I want to land on my intended app section after login. | Safe next values beginning with / are respected; unsafe redirects are rejected/ignored. | /login?next=/app%23factorlab | app/login/page.js; app/api/auth/login/route.js; lib/server/auth/session.js | P1 | Inventoried | Pending manual/browser test
BLS-009 | Authentication | Logout | As a signed-in user, I want to end my session. | Logout POST clears session state/cookie and returns the user to public/login state. | /api/auth/logout | app/api/auth/logout/route.js; components/public-home-experience.jsx | P1 | Inventoried | Pending manual/browser test
BLS-010 | Authentication | Forgot password | As a user, I want to request a password reset link. | Forgot password route accepts an email and triggers reset workflow; dev fallback is available only when explicitly configured. | /forgot-password | app/forgot-password/page.js; app/api/auth/forgot-password/route.js; lib/server/auth/session.js | P1 | Inventoried; smoke-tested | Browser smoke pass | RUN-006
BLS-011 | Authentication | Reset password | As a user with a reset token, I want to set a new password. | Reset page validates token/password and updates credentials through the reset API. | /reset-password | app/reset-password/page.js; app/api/auth/reset-password/route.js; lib/server/auth/session.js | P1 | Inventoried; smoke-tested | Browser smoke pass | RUN-006
BLS-012 | Access control | Private workspace guard | As an unauthenticated visitor, I should not access the private workspace. | Server-side auth redirects unauthenticated requests to login with a next path. | /app | app/app/page.js; lib/server/auth/session.js; middleware.js | P1 | Inventoried | Pending manual/browser test | RUN-006: unauthenticated /app redirects to /login?next=...
BLS-013 | Access control | Session API | As the frontend, I need current session/workspace identity. | Session API returns authenticated session payload or appropriate unauthorized response. | /api/v1/session | app/api/v1/session/route.js; lib/server/auth/session.js | P1 | Inventoried; smoke-tested | Browser smoke pass | RUN-006
BLS-014 | Access control | Early access page | As a gated user, I need a clear access page when workspace access is unavailable. | Access route renders an access-oriented page instead of exposing raw errors. | /access | app/access/page.js | P1 | Inventoried; smoke-tested | Browser smoke pass | RUN-006
BLS-015 | Workspace shell | Authenticated dashboard assembly | As a signed-in user, I want the private app to load my workspace dashboard. | The /app page fetches the workspace dashboard, builds session payload, and falls back to a limited-data dashboard if assembly fails. | /app | app/app/page.js; lib/server/dashboard-service.js; components/terminal-app.jsx | P1 | Inventoried | Pending authenticated browser test | RUN-006: unauthenticated /app redirects to /login?next=... | ISS-003
BLS-016 | Workspace shell | Sidebar navigation | As a user, I want to move between Today, Money, Portfolio, Diversification, Research, FactorLab, and Holdings. | Workspace sidebar updates active section and scrolls/hash-links to the selected panel. | /app#today | components/terminal-app.jsx WORKSPACE_NAV; components/workspace/shell.module.css | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-017 | Workspace shell | Hash deep links | As a user, I want URLs like /app#factorlab to open the correct section. | Hash handler maps known fragments to workspace sections and ignores unknown fragments safely. | /app#factorlab | components/terminal-app.jsx applyHashSection/selectWorkspaceSection | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-018 | Workspace shell | Workspace refresh | As a user, I want to refresh live dashboard data on demand. | Refresh control calls refresh endpoints, updates modules, and shows honest unavailable states on failure. | /app | components/terminal-app.jsx requestLiveRefresh/refreshWorkspace; app/api/refresh/route.js; app/api/internal/refresh/route.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-019 | Workspace shell | Limited-data fallback | As a user, I want the app to stay usable when backend data is unavailable. | Fallback dashboard shows limited-data messages instead of crashing or showing seeded market ideas as live data. | /app | app/app/page.js buildWorkspacePageFallback; lib/server/dashboard-service.js; tests-node/dashboard-service.test.mjs | P1 | Inventoried; automated coverage present | Automated pass | RUN-002 and/or RUN-005, depending on source test family
BLS-020 | Workspace shell | Compliance notice | As a user, I need to know the app is research/decision support, not advice. | Compliance notice is visible in workspace/public flows where decisions are shown. | /app | components/terminal-app.jsx ComplianceNotice; README.md | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-021 | Workspace shell | Guide and glossary | As a new user, I want a short guide and glossary to understand product terms. | Guide/glossary buttons open dismissible overlays; Escape closes glossary. | /app | components/terminal-app.jsx showWelcomeGuide/showGlossary; components/language-layer.jsx | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-022 | Language/UX | Dynamic Spanish cleanup | As a Spanish-language user, I should not see backend jargon or malformed mixed-language text. | Language layer and cleanWorkspaceCopy translate static/dynamic terms and suppress known bad strings such as [object Object], keep UUP, phantom, recoverability. | /app | components/language-layer.jsx; components/terminal-app.jsx cleanWorkspaceCopy; BLS_PRIME_PRODUCT_OVERVIEW.md | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-023 | Decision cockpit | Current answer panel | As a user, I want the first workspace screen to tell me what to do now. | TruthInterfacePanel shows current answer, summary, pillars, sources, and actions in human language. | /app#today | components/terminal-app.jsx TruthInterfacePanel | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-024 | Decision cockpit | Decision pillars | As a user, I want to see investable cash, real independence, and reserve/optionalidad together. | Three key metrics render with labels, tones, and fallbacks when data is missing. | /app#today | components/terminal-app.jsx TruthInterfacePanel; lib/server/decision-os.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-025 | Decision cockpit | Ask/explain action | As a user, I want to ask why the decision changed. | Chat/explain buttons open contextual chat without losing current workspace state. | /app#today | components/terminal-app.jsx TruthInterfacePanel; components/portfolio-chat.jsx | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-026 | Decision cockpit | Stage/defer/reject decision actions | As a user, I want to record a decision response without executing impulsively. | Primary actions call decisions/escrow endpoints, show pending/success/error states, and update dashboard payload. | /app#today | components/terminal-app.jsx stageAction/recordDecision; app/api/v1/workspaces/[workspaceId]/decisions/route.js; app/api/v1/workspaces/[workspaceId]/escrow/route.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-027 | Decision cockpit | Alerts | As a user, I want risk or data alerts surfaced clearly. | Alerts panel renders severity, title, and body from dashboard alerts without raw backend artifacts. | /app#today | components/terminal-app.jsx AlertsPanel; app/api/v1/workspaces/[workspaceId]/alerts/route.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-028 | Money plan | Finance plan editor | As a user, I want to enter monthly income, expenses, reserve, contribution target, and currency. | PersonalFinancePanel fields accept bounded numeric input and submit normalized finance plan payload. | /app#money | components/terminal-app.jsx PersonalFinancePanel/FinancePlanField; app/api/v1/workspaces/[workspaceId]/finance-plan/route.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-029 | Money plan | Investable cash calculation | As a user, I want to know how much can be invested without breaking the cash plan. | Panel computes investable cash, monthly spend, savings rate, target coverage, and visual allocation. | /app#money | components/terminal-app.jsx PersonalFinancePanel; lib/server/normalizers.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-030 | Money plan | Finance validation | As a user, I should get helpful validation if I enter invalid negative/empty values. | API parser rejects invalid negative values and returns user-facing validation errors. | /api/v1/workspaces/[workspaceId]/finance-plan | lib/server/workspace-action-validation.js parseFinancePlanPayload; tests-node/workspace-action-validation.test.mjs | P1 | Inventoried; automated coverage present | Automated pass | RUN-002 and/or RUN-005, depending on source test family
BLS-031 | Portfolio | Portfolio overview | As a user, I want a summary of total value, returns, benchmark comparison, and structural reading. | PortfolioPanel renders core metrics with fallback labels for missing cost basis/history/holdings. | /app#portfolio | components/terminal-app.jsx PortfolioPanel; components/workspace/formatters.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-032 | Portfolio | Performance chart range tabs | As a user, I want to change the range of portfolio history. | Range tabs update chart range and preserve section state. | /app#portfolio | components/terminal-app.jsx RangeTabs/PortfolioChart/PortfolioPanel | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-033 | Portfolio | Holdings table | As a user, I want to review holdings, roles, weights, values, and returns. | Holdings table renders positions with cleaned labels and handles empty/missing holdings honestly. | /app#holdings | components/terminal-app.jsx PortfolioPositionTable/PortfolioHoldingsPanel/HoldingsPanel | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-034 | Portfolio | Holdings editor | As a user, I want to add/update a holding directly. | Holdings draft sanitizes ticker/number inputs and POSTs normalized trade/holding instruction. | /app#holdings | components/terminal-app.jsx HoldingsPanel submitHoldingDraft/submitTradeInstruction; app/api/v1/workspaces/[workspaceId]/portfolio/route.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-035 | Portfolio | Portfolio validation | As a user, invalid holding updates should be rejected clearly. | Portfolio update payload requires a trade instruction and validates ticker/action fields before persistence. | /api/v1/workspaces/[workspaceId]/portfolio | lib/server/workspace-action-validation.js parsePortfolioUpdatePayload; tests-node/workspace-action-validation.test.mjs | P1 | Inventoried; automated coverage present | Automated pass | RUN-002 and/or RUN-005, depending on source test family
BLS-036 | Portfolio | Exposure and concentration views | As a user, I want to see sector/role exposures and concentration. | Exposure, donut, horizon, movers, and review panels summarize role/sector/concentration without raw JSON. | /app#portfolio | components/terminal-app.jsx PortfolioExposurePanel/PortfolioDonutPanel/PortfolioReviewPanel/PortfolioMoversPanel | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-037 | Portfolio | Transactions/history panel | As a user, I want to see recent portfolio transactions if available. | Transactions panel renders transaction rows or an empty state. | /app#portfolio | components/terminal-app.jsx PortfolioTransactionsPanel | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-038 | Diversification | Simple diversification reading | As a user, I want a simple visible-real-gap reading of diversification. | Simple panel runs or displays phantom diversification analysis and explains visible breadth, real breadth, and gap. | /app#diversification | components/terminal-app.jsx SimplePhantomDiversificationPanel; app/api/v1/workspaces/[workspaceId]/phantom-diversification/route.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-039 | Diversification | Editable diversification analysis | As a user, I want to edit the holdings included in the diversification test. | Advanced panel supports add/remove/reset rows, sanitized tickers/weights, and reruns analysis. | /app#diversification | components/terminal-app.jsx PhantomDiversificationPanel | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-040 | Diversification | Visible to real clock visual | As a user, I want a visual explanation of apparent versus real diversification. | DiversificationClockCard shows visible, real, and breach/gap values with correct tone labels. | /app#diversification | components/terminal-app.jsx DiversificationClockCard | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-041 | Diversification | Contributor table | As a user, I want to know which positions add independence versus repeat exposure. | Contributor rows label roles/tones and avoid untranslated phantom jargon. | /app#diversification | components/terminal-app.jsx contributorTone/contributorRoleLabel/PhantomDiversificationPanel | P1 | Inventoried; smoke-tested | Browser smoke pass | RUN-006
BLS-042 | Diversification | Diversification API validation | As a user, oversized or too-small holding lists should fail clearly. | API requires at least three holdings, validates tickers/weights, and rejects oversized lists with user-facing error. | /api/v1/workspaces/[workspaceId]/phantom-diversification | lib/server/workspace-action-validation.js parsePhantomDiversificationPayload; tests-node/phantom-diversification.test.mjs | P1 | Inventoried; automated coverage present | Automated pass | RUN-002 and/or RUN-005, depending on source test family
BLS-043 | FactorLab | Integrated FactorLab panel | As a workspace user, I want to screen candidates without leaving the app. | Integrated panel shows filters, rankings, explainability, and rejection/lookahead guard context. | /app#factorlab | components/terminal-app.jsx FactorLabWorkspacePanel | P1 | Inventoried; smoke-tested | Browser smoke pass | RUN-006
BLS-044 | FactorLab | Standalone FactorLab workstation | As a visitor/user, I want a standalone FactorLab explainer/workstation. | Standalone route renders FactorLabWorkstation with filters, candidate display, and educational context. | /factorlab | app/factorlab/page.js; components/factorlab-workstation.jsx; app/factorlab/factorlab.module.css | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-045 | FactorLab | Lookahead rejection demonstration | As a user, I want invalid future-looking calculations blocked or explained. | FactorLab separates valid filters from rejection view and explains why lookahead is invalid. | /factorlab | components/factorlab-workstation.jsx; components/terminal-app.jsx FactorLabWorkspacePanel | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-046 | Macro Brain | Macro Brain public/research page | As a user, I want a research-only macro snapshot page. | Macro Brain page loads live/snapshot macro data, formats dates/numbers, and states no trades are placed. | /macro-brain | app/macro-brain/page.js; lib/macro-brain-snapshot.js; lib/server/macro-brain.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-047 | Macro Brain | Macro Brain API | As the page/frontend, I need macro brain data through an API. | API returns normalized macro brain payload or unavailable state. | /api/macro-brain | app/api/macro-brain/route.js; tests-node/macro-brain-live.test.mjs | P1 | Inventoried; automated coverage present | Automated pass | RUN-002 and/or RUN-005, depending on source test family
BLS-048 | MOSAIC | MOSAIC observatory panel | As a user, I want a score-guide observatory of market structure when available. | Panel renders snapshot score guide and metrics without blocking core workspace if data is absent. | /app | components/terminal-app.jsx MosaicObservatoryPanel; lib/mosaic-observatory-snapshot.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-049 | Research | Equity research runner | As a user, I want to run an audited company research report for a ticker. | Research panel cleans ticker, starts async or direct research, polls status, and renders fallback if async unavailable. | /app#research | components/equity-research-panel.jsx; app/api/v1/workspaces/[workspaceId]/research/[ticker]/route.js; lib/server/equity-research.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-050 | Research | Research memo tab | As a user, I want a readable memo from deterministic research outputs. | Memo tab renders cleaned markdown and does not invent unavailable data. | /app#research | components/equity-research-panel.jsx renderMemo/cleanReportMarkdown | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-051 | Research | Valuation tab | As a user, I want DCF/reverse DCF/multiple context. | Value tab renders valuation metrics, scenarios, and confidence/coverage score. | /app#research | components/equity-research-panel.jsx renderValuation/ResearchMetric | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-052 | Research | Debate/agents tab | As a user, I want to see the internal debate and specialist stages. | Debate tab maps agent names to friendly names and shows stage states. | /app#research | components/equity-research-panel.jsx renderAgents/ResearchStage | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-053 | Research | Sources and audit tabs | As a user, I want sources, evidence ledger, gaps, and audit status. | Sources/Audit tabs show provider metadata, artifacts, coverage gaps, and audit tone. | /app#research | components/equity-research-panel.jsx renderEvidence/renderAudit/downloadArtifact | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-054 | Research | Research job persistence | As a user, I want research jobs to persist and retry safely. | Server persists local job id/backend mapping and handles completion/timeout fallback. | /api/v1/workspaces/[workspaceId]/research/[ticker] | lib/server/equity-research.js; tests-node/equity-research-jobs.test.mjs | P1 | Inventoried; automated coverage present | Automated pass | RUN-002 and/or RUN-005, depending on source test family
BLS-055 | Research | Stories endpoint | As a user, I want ticker story context when available. | Stories endpoint returns ticker story payload for the workspace. | /api/v1/workspaces/[workspaceId]/stories/[ticker] | app/api/v1/workspaces/[workspaceId]/stories/[ticker]/route.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-056 | Chat | Contextual portfolio chat | As a user, I want to ask questions about the current workspace state. | Chat opens from workspace, sends message with workspace context, streams/returns assistant answer, and supports close/stop. | /app | components/portfolio-chat.jsx; app/api/v1/workspaces/[workspaceId]/chat/route.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-057 | Chat | Chat input behavior | As a user, I want Enter to send and Shift+Enter to add a line. | Keyboard handler sends only intended messages and disables empty/pending submissions. | /app | components/portfolio-chat.jsx handleKeyDown/sendMessage | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-058 | Actions | Escrow/staged actions | As a user, I want actions staged before execution. | Escrow list shows active staged actions and supports execute/cancel PATCH/POST flows. | /app | components/terminal-app.jsx escrowItems/patchEscrow; app/api/v1/workspaces/[workspaceId]/escrow/route.js; app/api/v1/workspaces/[workspaceId]/escrow/[escrowId]/execute/route.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-059 | Actions | Decision ledger | As a user, I want recorded decisions and command history. | Decision/commands/ledger endpoints persist and return decision actions/history. | /api/v1/workspaces/[workspaceId]/ledger | app/api/v1/workspaces/[workspaceId]/decisions/route.js; app/api/v1/workspaces/[workspaceId]/commands/route.js; app/api/v1/workspaces/[workspaceId]/ledger/route.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-060 | Persistence | Watchlists | As a user, I want to retrieve and save watchlists. | Watchlists endpoint supports GET/POST for workspace-scoped watchlist state. | /api/v1/workspaces/[workspaceId]/watchlists | app/api/v1/workspaces/[workspaceId]/watchlists/route.js; lib/server/workspace-store.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-061 | Persistence | Saved views | As a user, I want to retrieve/save workspace views. | Saved views endpoint supports GET/POST and returns structured saved-view payloads. | /api/v1/workspaces/[workspaceId]/saved-views | app/api/v1/workspaces/[workspaceId]/saved-views/route.js; lib/server/workspace-store.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-062 | Persistence | Mandate/policy settings | As a user, I want portfolio mandate thresholds to be readable/editable. | Mandate endpoint validates bounded thresholds; policy endpoint exposes policy layer. | /api/v1/workspaces/[workspaceId]/mandate | app/api/v1/workspaces/[workspaceId]/mandate/route.js; app/api/v1/workspaces/[workspaceId]/policy/route.js; lib/server/workspace-action-validation.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-063 | Data modules | Dashboard module endpoints | As the frontend, I need individual workspace modules for lazy/detail refresh. | Module endpoints return normalized workspace submodules such as frontier, memory, alerts, repairs, twin, transitions, analogs, balance-sheet, legitimacy, failure modes. | /api/v1/workspaces/[workspaceId]/modules/[module] | app/api/v1/workspaces/[workspaceId]/modules/[module]/route.js and module routes; lib/server/dashboard-service.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-064 | Data modules | State/state-v2/state-contract endpoints | As an integrator, I need current state payloads and contract-shaped state. | State endpoints expose normalized current state and contract payloads. | /api/v1/workspaces/[workspaceId]/state | app/api/v1/workspaces/[workspaceId]/state/route.js; state-v2/route.js; state-contract/route.js; BLS_State_Contract_v1.md | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-065 | Data modules | Snapshot endpoint | As a client or tester, I need the current dashboard snapshot. | Snapshot route returns the latest dashboard snapshot artifact/payload. | /api/snapshot | app/api/snapshot/route.js; artifacts/dashboard/latest/dashboard_snapshot.json | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-066 | Streaming | Workspace stream endpoint | As the frontend, I need stream updates where supported. | Stream endpoint exposes workspace stream response without breaking clients if unavailable. | /api/v1/workspaces/[workspaceId]/stream | app/api/v1/workspaces/[workspaceId]/stream/route.js; lib/server/stream.js | P1 | Inventoried | Pending authenticated browser test |  | ISS-003
BLS-067 | Billing | Billing disabled behavior | As an early-access user, I should not enter broken billing flows. | Checkout, portal, and webhook return 410 billing_disabled while billing is frozen. | /api/billing/checkout | app/api/billing/checkout/route.js; app/api/billing/portal/route.js; app/api/billing/webhook/route.js | P1 | Inventoried | Pending manual/browser test
BLS-068 | Internal ops | Internal refresh auth | As an operator, I want internal refresh protected by token auth. | Internal refresh requires configured bearer token and rejects invalid/missing token. | /api/internal/refresh | app/api/internal/refresh/route.js; lib/server/internal-refresh-auth.js; tests-node/internal-refresh-auth.test.mjs | P1 | Inventoried; smoke-tested | Browser smoke pass | RUN-006
BLS-069 | Deployment | Vercel/Railway configuration | As an operator, I want documented env vars and deploy split. | README documents backend/frontend env vars, FMP split, SEC user-agent requirements, auth, and reset config. |  | README.md; vercel.json; railway.toml; Procfile; .env.example | P2 | Inventoried | Build pass only | RUN-003
BLS-070 | Data integrity | Backend snapshot selection | As the app, I want live snapshots preferred and stale/persisted snapshots handled explicitly. | Snapshot selector ignores stale live/persisted data unless configured to fall back. |  | lib/server/backend-snapshot.js; tests-node/backend-snapshot-selection.test.mjs | P1 | Inventoried; automated coverage present | Automated pass | RUN-002 and/or RUN-005, depending on source test family
BLS-071 | Validation | Workspace action validation | As a user, invalid commands should fail before corrupting state. | Payload parsers validate finance, portfolio, phantom, decision, escrow, and mandate updates with structured errors. |  | lib/server/workspace-action-validation.js; tests-node/workspace-action-validation.test.mjs | P1 | Inventoried; automated coverage present | Automated pass | RUN-002 and/or RUN-005, depending on source test family
BLS-072 | Config | Server config normalization | As a deployer, I want bare backend/app hosts normalized safely. | Config helpers normalize hosts/schemes and preserve explicit local schemes. |  | lib/server/config.js; lib/request-origin.js; tests-node/config.test.mjs; tests-node/request-origin.test.mjs | P2 | Inventoried; automated coverage present | Automated pass | RUN-002 and/or RUN-005, depending on source test family

## Test Runs
Run ID | Date | Scope | Command/Method | Result | Evidence | Features Covered | Notes
RUN-001 | 2026-06-21 | Inventory | Static route/component/API scan | Passed | rg --files app components lib tests-node tests; BLS_PRIME_PRODUCT_OVERVIEW.md reviewed | All inventoried rows | Initial tracker built from current code. Behavior testing not complete.
RUN-002 | 2026-06-21 | Node server/unit coverage | npm run test:web | Passed | 39 tests passed; 0 failed | Backend snapshot, config, dashboard service, equity research jobs, internal refresh auth, macro brain, phantom diversification, request origin, workspace action validation | Automated coverage only; not a full browser story pass.
RUN-003 | 2026-06-21 | Production build and route compilation | npm run build | Passed | Next.js build compiled successfully; 15 app routes generated; /app bundle built | Public routes, auth pages, /app, FactorLab, Macro Brain, API route compile surface | Build proves compilation, not behavioral UX correctness.
RUN-004 | 2026-06-21 | Python backend/research tests | python -m pytest tests | Failed | 50 passed, 21 setup errors; root cause PermissionError on C:/Users/T14 Ultra 7/AppData/Local/Temp/pytest-of-T14 Ultra 7 | Python tests blocked by temp-directory access before app assertions | Logged as logistical test-environment error.
RUN-005 | 2026-06-21 | Python backend/research tests after temp fix | python -m pytest tests | Passed | 71 passed, 0 failed after pyproject addopts --basetemp=.pytest_tmp | Allocator, dashboard, macro clients, equity research, feature fallbacks, phantom diversification, policy, reporting, spectral/tail-risk utilities | Warnings remain; no failing assertions.
RUN-006 | 2026-06-21 | Browser smoke: public and unauthenticated flows | Playwright/Chrome script against http://localhost:3000 | Passed | output/playwright/browser-smoke-results.json; screenshot output/playwright/home-spanish-smoke.png; 13 checks passed | Public home, Spanish default, language toggle, broken-copy scan, login, forgot/reset password pages, terms, FactorLab, Macro Brain, protected /app redirect, billing disabled endpoints | Three console 410s are expected billing_disabled responses.

## Issue Log
Issue ID | Feature ID(s) | Severity | Status | Summary | Observed Behavior | Expected Behavior | Evidence | Fix Commit/Files | Retest Evidence
ISS-001 | ALL | P2 | Open | Full manual/browser user-story pass not yet complete | Automated gates pass, but every story has not yet been exercised through browser/API behavior with observed evidence. | Each story should have explicit behavior test evidence, failures logged, fixes applied, and retest evidence. | Current goal continuation; initial artifact creation step |  | Pending
ISS-002 | Quality gates | P1 | Closed | Pytest default temp root inaccessible on this Windows profile | python -m pytest tests produced 21 setup errors before app assertions due PermissionError scanning %TEMP%/pytest-of-T14 Ultra 7. | Python tests should run from repo without depending on inaccessible user temp directory. | RUN-004 | pyproject.toml: addopts = --basetemp=.pytest_tmp | RUN-005: 71 passed, 0 failed
ISS-003 | Authenticated workspace stories | P1 | Open | Authenticated browser testing requires local auth/storage configuration | Public/protected redirect flows can be tested, but entering /app as an authenticated user requires Neon storage and BLS_PRIME_AUTH_SECRET/DATABASE_URL configuration. | Full user-story test loop needs a configured test account/workspace or a local auth fixture. | lib/server/auth/session.js requires usingNeonStorage and BLS_PRIME_AUTH_SECRET; .env.example documents empty values |  | Pending configured test account or local auth fixture